## Risk log
Project: Hobbies Website
Risk description | Impact if the risk occurs | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Contingent action Action to be taken if the risk happens. | Progress on actions | Impact after mitigation/ contingent action is taken
Project foundations such as database and schema are not well-defined. | High | carry out short agile iterations and get feedback early on! | Escalate to the trainer to determine the specification required for the project | obtain project specification with clear deliverables | low
Not being experienced in software development or familiar with how to use given technology and best practices needed, could lead to delay in completion. | High | do short agile sprints, fail fast and learn from mistakes | discuss with trainers and get help as early as possible |  | low
Project schedule is not clearly defined or understood | low | we have a table of milestones to ensure project is delivered on time Go through upcoming tasks in a weekly project progress review. | Revisit the schedule wih the trainer. 'Relaunch' the schedule. | meet with trainer to duscuss | low
Estimating and/or scheduling errors | High | Use story points to allocate units of work to tasks, however as a beginner this maynot be the most accurate, so use the milestones laid out as an aide to help meet deadline | Escalate to trainer and inform them of the delay Raise change request for change to budget or schedule. Pull down contingency. | agree on a plan on how to proceed with trainer. | medium
developing new features during project may increase risk of not meeting deadline | High | Read and understand full scope of work and communicate with the trainer before and during project to avoid delays. | Escalate to the trainer with plan of action, including impact on time and quality. | come up with an altered schedule and feedback to trainer | High
Inadequate Junit testing leads to a programme that doesn't execute well | Medium | Ensure test cases/quality checks are done correctly | Raise risk immediately and raise issue if it is clear that testing inadequate or not working | solve issues by seeking help needed | Medium
Make sure the database is deploying correctly | Medium | Ensure end user tests have been carried out to make sure application and database are deploying asd expected | Make a plan to test the deployment | retest to see if application and database are working | Medium
Application and database security | High | Ensure databases and application are secure and mitigate potential for hacking as much as possible. limiting the power of user accounts may give a hacker a harder time in taking complete control of the database. Protect against SQL-injection threats are to protect web-facing databases with firewalls and to test input variables for SQL injection during development. | speak with trainer and try to put measures in places to prevent future attacks | update trainer on the implementations | High
lack of OOP and SOLID principle implementation could result in poor code and eventual user experience. | High | try to get a good grasp of the principles before the project begins and revist concepts that are not clear | seek additional material to understand difficult concepts | inform trainers | High
Lack of OOP principles could mean the project code is diffcult to read and maintain. | Medium | get short sections of code checked for OOP principle implementation as you go | communicate with trainers about this to reduce having to implement at the end. |  | Medium
QA Academy
QA Consulting

## Severity Table
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High